## V1
Project Development and Completion Tracker
Porject ID: Version 1.2 (Flutter)
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers | Nishith Jain |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
|  |  |  | Om Thorve |  | Team Lead
Front/Back End
|  |  |  | Sudhamsu Rawlo |  | Team Lead
Back End
Front End
Epic:
Story 1:
Story 2:
Story 3:
Task1: | Write a review (survey) paper from the research papers found for references and literature survey
Task2: | Research about how can the EEG signals be used for simple tasks like moving a toy car or switching a light (on/off)
Task3:
Task4:
Task5:
Task6:
Acceptance Criteria:
1
2
3
4
5
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Survey Paper writing | Find relevant research papers | Complete | Nishith, Om, Sudhamsu | 2024-08-10 | 2024-08-17 | 2024-08-10 | 2024-08-17 | 100% | Not Started | Medium
|  | Write a survey paper | In Progress | Sudhamsu | 2024-08-23 | 2024-09-20 |  |  | 0%
| Research on application of EEG signals for simple tasks | Research | In Progress | Nishith, Om | 2024-08-23 | 2024-09-20 | 2024-08-23 |  | 25% | In Progress | Low
[10 empty] | Complete | High
Sprint 1 | [9 empty] | On Hold
Overdue
12
10
10
10
10
15
15
20
20
20
20
10
20
20
15
15
10
20
20
15
15
20
342
65
407

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2